PEACEHAVEN and TELSCOMBE REGENERATION  PARTNERSHIP

YOUR TOWN YOUR SAY -  REVISITED

| # Objective | # Outcome | # Action Required | Action Taken |  |  |
| --- | --- | --- | --- | --- | --- |
| 1. Create a heart for the community | a) Improve Meridian Centre | Meeting with owners/people responsible Purchase freehold Build double storey car park Turn into attractive shopping centre with community facilities | Together with LDC -have met with new owners, Co-op Ongoing Tactile paving Lights on ramp to North end of centre Refurb. toilets |  |  |
|  | b) Improve Joff (new café/cyber café)) | Link to Meridian centre Provide cinema Develop building to provide community mtg place | Joff to undergo a refurb. See below Working with YDS to increase opening times |  |  |
|  | c) Develop local community facilities | Awareness raising mtgs at local level to discuss needs Purpose built House Project building Develop North P/haven | Youth survey and sub group formed Presentations to groups HP represented on P’ship Represented on P’ship |  |  |
|  | d) Voluntary groups: central recource co-ordination of voluntary group more funding for voluntary groups | Expand H P to P/haven CVS Employ someone to raise funds | Volunteer Bureau managed by House Project Development workers to be employed through 2nd home council tax |  |  |
|  | e) Minor injuries clinic |  |  |  |  |
| 2. Improve transport | a) Reduce congestion on Sth CR | Cheaper public transport | P’ship represented on LD Transport Group |  |  |
|  | b) Shuttle bus to Meridian Ctr | New hopper bus route |  |  |  |
|  | c) New bus terminus | Design feasibility study | Additional bus on Sth. Coast Rd 14c now goes to hospital |  |  |
|  | e) New bus routes to hospital and rail | Hopper bus as above |  |  |  |
|  | f) Bus shelters | New buses, lower floor Design F/Study |  |  |  |
|  | g) disabled access to shops, hospitals and schools |  | All schools have disabled access |  |  |
|  | h) cycle lanes | F/Study | Part of bus route consultation |  |  |
|  | k) Upgrade pavements esp Arundal Rd | Lobby ESCC |  |  |  |
|  | l) New bypass | Lobby as above |  |  |  |
| 3. Improve social facilites | a) Child care facilities: after school club breakfast club drop-in creche – for accessing Meridian Ctr etc. | More registered childminders Involve school heads Contact PTAs F/Study Contact EYDCP | Sure Start Boomerang Kids in Saltdean |  |  |
|  | b) More youth facilites/programmes | Identify needs Skate board convention Beach festival Music festival Facilities/activites for mums Develop cultural and arts based prog. to link into entertainment centres in Brighton and EAstbourne | Youth survey Youth sub group Working with YDS Low Tide ‘The Circle’ part of Telscombe Town Fair Discuss with LDC Cultural services |  |  |
|  | c) Increase access to adult learning | Work with P/Haven & Telscombe Learning P’ship | Adult education classes running at Tels.CC and Meridian Cente House Project – IT courses |  |  |
| 4. Improve sports and leisure facilities | a) New swimming pool | Identify new location |  |  |  |
|  | b) Ten pin bowling | Not needed till current facilites are in full use |  |  |  |
|  | c) Cricket pitch, hockey, athletics, all weather pitch | Identify land all in one place - lobby | LDC sports development |  |  |
|  | d) Reduce cost of existing facilites | Local council subsidies |  |  |  |
|  | e) New Cinema/theatre | Liaise with T/Clerk regarding present proposals | New seating and sound/lighting in Meridian Hall – grant from P’ship |  |  |
| 5. Improve security | a) Improve neighbourhood watch scheme | Increase no. of members Publicise mtgs | Neighbourhood watch boundaries aligned to police boundaries Police attend N/watch meetings Rep from NW attended P’ship |  |  |
|  | b) Increase police patrols | Further investigation | Community support officers Community Wardens |  |  |
|  | c) Manned police station | As above | Yes |  |  |
| 6) New community facilites | a) PH museum | Locate building |  |  |  |
|  | b) Cemetery Garden of rememberance | Find site | Investigate Meridian Park |  |  |
|  | c) Better recycling | Pressure on local authorities | Kerbside collection |  |  |
| 7. Landscaping improvements | a) Cliff reinforcements | EA | Shoreline management consultation |  |  |
|  | b) Beach improvements | English Nature MAFF LDC ESCC |  |  |  |
|  | c) Planting, seating and fencing | P/haven & Telscombe Town Councils |  |  |  |
|  | d) Allotments |  |  |  |  |