Lewes Local Strategic Partnership

# Children and Young People’s Working Group

# Objectives July 2005

## Objective 1: To improve the collation and dissemination of information regarding activities and services for children and young people

| Action | Outcome | Date for completion | Who is responsible |
| --- | --- | --- | --- |
| 1.1 To organise a survey by young people on LSP young people’s page and links to other related websites | Website which is young person friendly and easily navigable | October 2005 | YDS |
| 1.2 Maintain an ongoing dialogue with Connexions regarding the quality of their website for young people | Website which is young person friendly and easily navigable | Ongoing |  |
| 1.3 Continue with the collection of dissemination of activities for young people | Each partner organisation is aware of what is happening for young people in the Lewes Area | Ongoing | YDS / partner organisations |

Objective 2: To identify gaps in the provision of activities and services for children and young people and to also identify potential delivery and funding opportunities

| Action | Outcome | Date for completion | Who is responsible |
| --- | --- | --- | --- |
| 2.1 To ensure links between this group, LPCs and children and young people planning groups | Clear lines of communication and avoidance of duplication of plans | July 2005 ongoing | Sally Harper/Penny Shimmin/Jan Murphy |
| 2.2 To collect information about gaps in provision for children and young people from group members and local partnership chairs | A clear understanding of the gaps in provision to inform future plans | July 2005 ongoing | Sally Harper/ Jan Murphy |
| 2.3 To link plans for services for young people | A clear understanding of the services that are being planned for young people and the gaps in provision | July 2005 ongoing |  |

Objective 3: To identify and consider solutions to the concerns of children & young people about feeling safe within their schools and communities

| Action | Outcome | Date for completion | Who is responsible |
| --- | --- | --- | --- |
| 3.1 To put the issue of youth safety on the CRP agenda | Discussion at strategic level regarding the concerns of young people about personal safety | September 2005 |  |
| 3.2 To put together a personal safety strategy for young people | A wide ranging package of interventions with young people focusing on personal safety to include: looking after personal belongings; road safety; safer drinking etc. | April 2006 |  |

Objective 4: To identify the need for venues (including buildings and green spaces for activities for children and young people

| Action | Outcome | Date for completion | Who is responsible |
| --- | --- | --- | --- |
| 4.1 To undertake a survey within the group of availability of buildings and green spaces | Optimum use of existing facilities | December 2005 |  |
| 4.2 To canvass the chairs of all partnerships to ascertain what the gaps are in their areas | Clear understanding of what is available and what is needed | December 2005 |  |

Objective 5: To identify the ways that transport services assist children and young people to socialise and access services

| Action | Outcome | Date for completion | Who is responsible |
| --- | --- | --- | --- |
| 5.1 To canvass the chairs of all partnerships what the issues are for young people in their area | Clear understanding of what is available and what is needed | December 2005 |  |
| 5.2 To liaise with the Transport Action Group about monitoring and consultation with young people on whether the transport plan is working for them | The outstanding needs will be identified | December 2005 |  |

Objective 6: To promote the positive contribution children and young people make to their communities

| Action | Outcome | Date for completion | Who is responsible |
| --- | --- | --- | --- |
| 6.1 To investigate the setting up of a Youth Bank project for young people in the Lewes Area | Involvement of young people funding projects | September 2005 | Lloyd Russell-Moyle |
| 6.2 To investigate the setting up of a local youth accreditation scheme | The involvement of young people is recognised and celebrated | September 2005 | Lloyd Russell-Moyle |
| 6.3 To put on training for adults and young people in writing press releases | High quality and constant press releases fed to the press | December 2005 |  |
| 6.4 To undertake one inter-generational project in the area | Breaking down of stereotypes and a more positive image of young people being portrayed | March 2005 |  |

Objective 7: To promote an inter-agency approach to positive parenting skills (On hold)

JM 14/07/05